Project Summary

Build a web platform where users can:

- Launch vulnerable practice labs (Docker containers)

- Run guided security exercises (or free-form)

- Capture tool output/logs (Nmap, Nikto, SQLmap, etc.)

- Get AI-generated explanations, “what to try next,” and remediation guidance

- Export a final report (PDF/HTML)

Core Modules

- Frontend Web App

  - Login, roles, dashboard

  - Lab launch/control UI

  - Log viewer + AI feedback panel

- Backend API

  - Auth + role-based access

  - Session management

  - Lab orchestration endpoints

  - Logging + storage

- Lab Orchestration (Docker)

  - Prebuilt vulnerable labs (e.g., DVWA, Juice Shop, WebGoat)

  - Start/stop/reset labs per session

  - Network isolation + resource limits

- Data Layer

  - Postgres or SQLite

  - Store sessions, users, commands, tool outputs, and AI responses

- AI Coach Layer

  - Takes tool output + session context

  - Returns explanation, risk, next steps, mitigation

  - “Safety mode” so it teaches without enabling real-world abuse

Team Roles

1) Tech Lead / Backend + AI

- Own FastAPI architecture, endpoints, and session model

- Design AI prompt pipeline + guardrails

- Integrate logging + report generation

2) Frontend Engineer

- GUI (dashboard, lab control, log viewer)

- Authentication flow + role UI

- Polished demo-ready UX

3) DevOps / Orchestration Engineer

- Docker lab templates + compose profiles

- Sandbox networking (internal network, no outbound)

- Deployment (local + optional cloud)

4) Security Content Engineer

- Curate 2–3 labs + 6–10 guided “missions.”

- Define success criteria per mission

- Write safe, educational steps + expected outputs

5) Data / QA Engineer

- Database schema + migrations

- Testing (pytest) + API tests

- Metrics: session completion, common findings, AI usefulness scoring

MVP Scope (what we MUST finish)

MVP = demoable + gradable

- Login + roles (admin, creator, viewer)

- Launch 1 vulnerable lab

- Create a session

- Capture at least 2 tool outputs (e.g., Nmap + Nikto)

- AI feedback for outputs

- Session report export

Stretch Goals (only if ahead)

- Live log streaming (WebSockets)

- More labs + lab marketplace

- Scoring/rubric (points per finding)

Approximate Timeline (14 Weeks, this is just me yapping )

Week 1: Project Setup & Requirements

Deliverables

- Final feature list (MVP vs stretch)

- Repo + branching rules

- Tech stack decided

- Basic UI wireframe

Everyone does

- Pick roles + responsibilities

- Define 1-2 labs you’ll support (I can just take example labs from my ethical hacking class)

Week 2: System Design

Deliverables

- Architecture diagram

- Database ERD

- API endpoint list

- UI component list

Backend

- FastAPI skeleton + health check

Frontend

- React skeleton + routing

DevOps

- Docker lab chosen + runs locally

Week 3: Authentication + Database

Deliverables

- Users table + sessions table

- JWT login

- Role-based access working

Checkpoint: Admin can create users, and users can log in.

Week 4: Lab Orchestration v1

Deliverables

- Start/stop/reset lab via API

- Lab status endpoint

- Frontend button to launch lab

Checkpoint: “Launch lab” works from the web UI.

Week 5: Session Logging

Deliverables

- Create session + save tool outputs

- Log viewer UI

- Basic data persistence end-to-end

Checkpoint: Run tool  paste/upload output  saved & visible in UI.

Week 6: AI Coach v1

Deliverables

- AI prompt template + output format (JSON)

- “Explain this output” feature in UI

- Store AI responses per log

Checkpoint: AI gives a readable explanation + risk, + next-step suggestions.

Week 7: Guided Missions (Content)

Deliverables

- 3–4 missions for your chosen lab

- Each mission: goal, hint, expected output, remediation notes

Checkpoint: A new user can follow missions end-to-end.

Week 8: Midpoint Demo / Integration Polish

Deliverables

- End-to-end demo script

- Fix broken flows

- Improve UI clarity

Checkpoint: Smooth demo from login  lab  mission  AI feedback.

Week 9: Report Generation

Deliverables

- Export session report (PDF or HTML)

- Include findings + evidence + remediation + AI summary

Checkpoint: Click “Export Report” and it downloads a real report.

Week 10: Testing + Security Hardening

Deliverables

- Pytest tests for core endpoints

- Input validation (sanitize outputs)

- Lock labs to internal network (avoid misuse)

Week 11: Usability & Final Features

Deliverables

- UI improvements

- Role features refined (creator can publish missions, viewer read-only)

- Better error handling + 404 pages + loading states

Week 12: Final Demo Build

Deliverables

- “Gold path” demo ready

- Backup plan if cloud fails (local demo)

Week 13: Documentation + Presentation

Deliverables

- README (setup, run, architecture)

- Slides outline

- Individual contribution write-ups

Week 14: Final Presentation & Submission

Deliverables

- Final live demo / recorded video

- Final report + code submission

Recommended Tech Stack

- Backend: FastAPI + SQLAlchemy + Alembic + PostgreSQL

- Frontend: React + Vite

- Auth: JWT

- Labs: Docker Compose profiles

- AI: Local model (Ollama) or API

- Testing: pytest + httpx

- Report: HTML  PDF (or just HTML export)